## PERT CHART
PROJECT: 101Circle
LOCATION : Golf Course, Gurugram
COMMENCEMENT DATE: 1st April, 2026
PROPOSED LAUNCH : 30th AUGUST 2026
|  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER
ACTIVITIES | RESPONSIBILITY | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
INTERNAL RESEARCH AND CONCEPTULISATION | bar: APRIL WEEK 1 to MAY WEEK 1; JUNE WEEK 1; JULY WEEK 1 to AUGUST WEEK 1; SEPTEMBER WEEK 1
PERT CHART & INDICATIVE TIMELINES | SI | bar: APRIL WEEK 1
RESEARCH REPORT | SI | bar: APRIL WEEK 1 to APRIL WEEK 3
CONCEPT NOTES - 2 | SI | bar: APRIL WEEK 3 to MAY WEEK 1
ARCHITECTURAL AND INTERIOR EXCEUTION | bar: APRIL WEEK 1 to MAY WEEK 1; JUNE WEEK 1; JULY WEEK 1; AUGUST WEEK 1; SEPTEMBER WEEK 1
RECOMMEND ARCHITECT | SI/101CIRCLE | bar: APRIL WEEK 1
ClOSING THE ARCHITECT | SI/101CIRCLE | bar: APRIL WEEK 2
PLAN SERVICES | ARCHITECT/CONTRACTOR/101CIRCLE | bar: APRIL WEEK 2 to APRIL WEEK 3
IDENTIFY AND REVIEW SITE LAYOUT WITH F.O.H. AND B.O.H. SPACE ALLOCATION | SI/ ARCHITECT/101CIRCLE | bar: APRIL WEEK 3 to APRIL WEEK 4
REVIEW INTERIOR LAYOUT & MOODBOARD | SI/ ARCHITECT/101CIRCLE | bar: MAY WEEK 1 to MAY WEEK 2
REVIEW INTERIOR 3Ds | SI/ ARCHITECT/101CIRCLE | bar: MAY WEEK 2 to MAY WEEK 4
REVIEW FURNITURE LAYOUT/ DOCKET | SI / ARCHITECT/101CIRCLE | bar: MAY WEEK 4 to JUNE WEEK 1
IDENTIFY FURNITURE, SOUND, HVAC AND LIGHTING VENDORS | SI / ARCHITECT/101CIRCLE | bar: MAY WEEK 4 to JUNE WEEK 1
SAMPLING, ORDERING AND PRODUCTION OF THE FURNITURE | ARCHITECT/101CIRCLE | bar: JUNE WEEK 1 to JULY WEEK 4
OVERALL SITE FIT OUT | ARCHITECT/CONTRACTOR/101CIRCLE | bar: MAY WEEK 4 to AUGUST WEEK 1
GRAPHIC DESIGN COLLABORATION | bar: APRIL WEEK 1 to MAY WEEK 1; JUNE WEEK 1; JULY WEEK 1; AUGUST WEEK 1; SEPTEMBER WEEK 1
SUGGEST GRAPHIC DESIGNER/ BRANDING AGENCY | SI | bar: APRIL WEEK 1
CLOSE GRAPHIC DESIGNER | SI/101CIRCLE | bar: APRIL WEEK 1 to APRIL WEEK 2
NAMES & LOGOS FINALISATION | SI/101CIRCLE/DESIGNER | bar: APRIL WEEK 3 to MAY WEEK 1
MOODBOARD DEVELOPMENT | SI/101CIRCLE/DESIGNER | bar: MAY WEEK 2 to MAY WEEK 3
KEY COLLATERALS- MENU, COASTERS, MATS, NAPKINS | SI/101CIRCLE/DESIGNER | bar: MAY WEEK 3 to JUNE WEEK 2
TABLE SETTING PRESENTATION | SI | bar: JUNE WEEK 1 to JUNE WEEK 4
SAMPLING AND PRODUCTION OF ALL THE COLLATERALS | 101CIRCLE/DESIGNER | bar: JUNE WEEK 1 to JULY WEEK 2
SAMPLING AND FINALISATION OF TEAM UNIFORMS AND DIFFERENTIATION | SI/101CIRCLE/DESIGNER | bar: JUNE WEEK 1 to JUNE WEEK 3
PACKAGING AND DISPOSABLES | SI/ 101CIRCLE/ DESIGNER | bar: JUNE WEEK 2 to JUNE WEEK 3
KITCHEN OUTLET PLANNING | bar: APRIL WEEK 1 to MAY WEEK 1; JUNE WEEK 1; JULY WEEK 1; AUGUST WEEK 1; SEPTEMBER WEEK 1
RECOMMEND AND CONFIRM KITCHEN VENDOR | SI/101CIRCLE | bar: APRIL WEEK 2 to APRIL WEEK 3
DETAILED KITCHEN LAYOUT | SI/KITCHEN VENDOR | bar: MAY WEEK 1 to MAY WEEK 2
REVIEW SERVICES, MEP AND HVAC DRAWING | SI/KITCHEN VENDOR | bar: MAY WEEK 1 to MAY WEEK 2
SELECTION AND OPTIMISATION OF KITCHEN EQUIPMENT | SI/101CIRCLE/KITCHEN VENDOR | bar: MAY WEEK 3 to JUNE WEEK 1
KITCHEN EQUIPMENT PRODUCTION AND INSTALLATION | SI/101CIRCLE/KITCHEN VENDOR | bar: JUNE WEEK 2 to JULY WEEK 3
KITCHEN EQUIPMENT TESTING AND TRAINING | KITCHEN VENDOR | bar: JULY WEEK 4
CUISINE IDENTITY | bar: APRIL WEEK 1 to SEPTEMBER WEEK 1
FOOD MASTER MENUS WITH VISUAL REPRESENTATION | SI | bar: MAY WEEK 2 to JUNE WEEK 1
SAMPLING, FINALISATION & PRODUCTION OF CROCKERY AND CUTLERY | SI/101CIRCLE/HEAD CHEF | bar: JUNE WEEK 2 to JULY WEEK 4
TASTINGS - FOOD TRIALS | SI/101CIRCLE/HEAD CHEF | bar: AUGUST WEEK 1 to AUGUST WEEK 2
PRESENTATION AND SERVING STYLE | SI/101CIRCLE/HEAD CHEF | bar: AUGUST WEEK 2 to AUGUST WEEK 3
NOMENCLATURE AND DISCRIPTIONS | SI | bar: AUGUST WEEK 2 to AUGUST WEEK 3
ASSIST WITH FOOD COSTING AND FORMAT | SI/101CIRCLE/HEAD CHEF | bar: AUGUST WEEK 2 to AUGUST WEEK 3
PRICE AND PORTIONING | SI/HEAD CHEF | bar: AUGUST WEEK 2 to AUGUST WEEK 3
MENU TRAINING | SI/101CIRCLE/HEAD CHEF | bar: AUGUST WEEK 2 to AUGUST WEEK 3
AID IN F&B STYLING AND PHOTOGRAPHY | SI/101CIRCLE/HEAD CHEF | bar: AUGUST WEEK 4
CORE STRUCTURE AND HIRING | bar: APRIL WEEK 1 to MAY WEEK 1; JUNE WEEK 1; JULY WEEK 1; AUGUST WEEK 1; SEPTEMBER WEEK 1
PROVIDE OPTIMUM STAFF STRENGTH AND PAYROLL STRUCTURE | SI | bar: MAY WEEK 1
FLOAT CORE HIRING REQUIREMENTS TO MULTIPLE AGENCIES | SI | bar: MAY WEEK 1 to MAY WEEK 2
ASSIST WITH INTERVIEWS, TRADE TESTS AND SELECTION OF KEY POSITIONS- SOUS CHEF /CDP / HEAD MIXOLOGIST/ RM | SI/HR RECRUTER/ 101CIRCLE | bar: MAY WEEK 1 to JULY WEEK 4
TRAINING & OPERATIONS
PRE OPENING CHECKLIST | SI | bar: AUGUST WEEK 2
RECOMMEND POS SOFTWARE AND HARDWARE VENDORS | SI | bar: AUGUST WEEK 2
ASSIST WITH SERVICE TRAINING | SI | bar: AUGUST WEEK 2
KITCHEN & SERVICE TRAINING ON THE CONDUCT & MENUS | SI | bar: AUGUST WEEK 2
ASSIST WITH DOCUMENTATION & MANUALS | SI | bar: AUGUST WEEK 2
PROVIDE PRE OPENING CHECKLIST | SI | bar: AUGUST WEEK 2
SOFT LAUNCH | bar: AUGUST WEEK 3
PLEASE NOTE:
The Third-Party Vendor Timelines Could Vary